**A close up of a logo

Description automatically generated**

|  |  |  |  |
| --- | --- | --- | --- |
| **2025 SRC Elections Schedule** | | | |
| **Month** | **Date** | **Activity** | **Responsible** |
| July 2025 | 04 July | Submission of  Election Schedule and Electoral Committee names | Director Student Life and Governance |
| Week of  7-11 July | Approval of Election Schedule and Electoral Committee names | SED: University Relations, Sport & Student Affairs |
| Prepare for marketing of nominations | Student Life and Governance |
| Prepare nomination forms | Student Life and Governance |
| Prepare for marketing of voting | Student Life and Governance |
| Thursday,17 | Briefing and Conclusion of Service Level Agreement with the EC | Senior Director: Student Affairs |
| Monday 21 | Marketing of Elections and Nominations starts | Electoral Committee |
| Voter education starts | Student Life and Governance |
| Friday, 25- 16:00 | Nominations close | Electoral Committee |
| Monday, 28 | Control of Nominations starts | Electoral Committee |
| Aug 2025 | Friday, 01 | Publish first list of contestants | Electoral Committee |
| Wednesday, 06 | Disapproved candidates correct nominations | Electoral Committee |
| Friday,08.-16:00 | Submission of corrected nomination closes | Electoral Committee |
| Monday, 11 | Control of corrected nominations starts | Electoral Committee |
| Friday, 15 | Publish second list of contestants | Electoral Committee |
| Monday,18 -16:00 | Submission of appeals on nominations closes | Electoral Committee |
| Monday, 25 | Senior Executive Director: Student Affairs finalise appeals on nominations | SED: University Relations, Sport & Student Affairs |
| Wednesday, 27 | Publish final list of contestants | Electoral Committee |
| Marketing of Voting and Campaigning start |
| Friday, 29 | Submit candidate details for preparation of electronic ballot | Electoral Committee |
| Sep 2025 | Wednesday, 03 | Approval of sample ballot paper | Electoral Committee |
| Monday, 08 | Uploading of electronic ballot starts | Corporate Governance |
| Reinforcing of Marketing of Voting | Student Life and Governance |
| Wednesday, 10 | Confirm Uploading of electronic ballot completes | Corporate Governance |
| September, 15 | Testing of the system starts | Student Life and Governance |
| September, 18 | Testing of the system ends | Student Life and Governance |
| Oct 2025 | Friday, 03 | Manifesto sessions | Electoral Committee |
| Wednesday, 08 | Voting starts | Corporate Governance & EC |
| Thursday, 09 | Voting continues | Corporate Governance & EC |
| Friday,10 - 17:00 | Voting closes | Corporate Governance & EC |
| Counting of votes | Corporate Governance |
| Announcement of provisional results | Corporate Governance & EC |
| Tuesday,14 - 16:00 | Submission of objections closes | Electoral Committee |
| Thursday,16 -16:00 | Electoral Committee finalises objections | Electoral Committee |
| Monday, 20 - 16:00 | Submission of appeals on voting and results closes | Electoral Committee |
| Friday,24 - 16:00 | Senior Executive Director: Student Affairs finalise appeals on voting and results | SED: University Relations, Sport & Student Affairs |
| Wednesday, 25 | Announcement of results | Electoral Committee |
| Tuesday, 28 | Constituting of campus SRCs and UJSRC | Electoral Committee |
| Nov | Monday, 01 | Submission of report by the EC | Electoral Committee |
| Friday, 28 | Induction of the newly elected SRC | Student Life and Governance |
| Saturday, 29 | Induction of the SRC continues | Student Life and Governance |
| Sunday, 30 | End of Induction of the SRC | Student Life and Governance |
| Jan 2026 | Monday, 1 | Start of the Term of Office | Student Life and Governance |